## Setup
cod_emp | Name | Level | Hour Rate
1 | Simon Gallo | Supervisor | 50
2 | Nigel Dow | Supervisor | 50
3 | Jack Schwarz | Installer | 40
4 | Federico Crespo | Installer | 30
5 | Ayrton Mittica | Installer | 30
6 | Frank Falcon | Installer | 30
7 | Turei Haronga | Installer | 30
code_ass | Asset
1 | Terminal Ends
2 | QuickLinks (Barriers)
3 | Quartgards
cod_del | Delay
1 | Internal
2 | External
3 | No delays
cod_haz | Hazard
1 | Internal
2 | External
cod_cli | Client
1 | Coates
2 | CPB

## Dashboards
[10 empty] | GOaLS VS ACHIEVED [KM] |  |  | Installed Assets
|  | challenge the status quo | [7 empty] | 0.56 | 0.56 |  | 1 | 0 | 1
[10 empty] | 100% |  |  | Quick Links | Terminal Ends | Quart Gards
Delays |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
|  | Goal[Km] | 0 | 0 | 0 | 0 | 0.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.56
Internal | External | Achieved [Km] | 0 | 0 | 0 | 0 | 0.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.56
|  | Progress | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
0 | 2

## Data
Code/ID | Start Date | End Date | Hours | Delays | Type of delays | Possible Savings for delays | Name | Level | Goal [metres] | Goal [Kilometres] | Achieved [metres ] | Achieved [Km] | Bal to Achieved [mtr] | Bal to Achieved [km] | Client | Hazards Detected | Type of Hazards | Estimated Costs | Year | Month | Date
1001 | 2020-05-11 19:30 | 2020-05-12 04:00 | 8.5 | 2 | External | 100 | Simon Gallo | Supervisor | 560 | 0.56 | 560 | 0.56 | 0 | 0 | CPB | 1 | External | 425 | 2020 | May | 5/11
| 2020-05-11 19:30 | 2020-05-12 04:00 | 8.5 | 2 | External | 60 | Federico Crespo | Installer | 560 | 0.56 | 560 | 0.56 | 0 | 0 |  |  |  | 255 | 2020 | May | 5/11
| 2020-05-11 19:30 | 2020-05-12 04:00 | 8.5 | 2 | External | 60 | Ayrton Mittica | Installer | 560 | 0.56 | 560 | 0.56 | 0 | 0 |  |  |  | 255 | 2020 | May | 5/11
| 2020-05-11 19:30 | 2020-05-12 04:00 | 8.5 | 2 | External | 60 | Frank Falcon | Installer | 560 | 0.56 | 560 | 0.56 | 0 | 0 |  |  |  | 255 | 2020 | May | 5/11
1002 |  |  | 0 |  |  | #N/A |  | NOT FOUND |  | 0 |  | 0 | 0 | 0 |  |  |  | #N/A

## Assets Installed
Assets Installed | S#? | Date
Terminal Ends

## Analysis
Estimated Costs per employee
Sum of emplyees | Month
Employee | May | Total
Ayrton Mittica | 255 | 255
Federico Crespo | 255 | 255
Simon Gallo | 425 | 425
Frank Falcon | 255 | 255
Total | 1190 | 1190
Orders for Clients
Client | Count
Coates
CPB | 1
Total | 1
Estimated Costs for Delays
Sum Possible Savings for delays | Column Labels
Name | May | Total
Ayrton Mittica | 60 | 60
Federico Crespo | 60 | 60
Simon Gallo | 100 | 100
Frank Falcon | 60 | 60
Total | 280 | 280
Total Hours per employee
Name | Shours
Ayrton Mittica | 8.5
Federico Crespo | 8.5
Simon Gallo | 8.5
Frank Falcon | 8.5
Total | 34
Assets Installed
Asset | Count
Terminal Ends | 1 | Terminal Ends | 1
Total | 1 | Total | 1
|  | 0 | 0
|  | Total | 1
Hazards
Type | Count
External | 1
Total | 1
Delays
Internal | NO BORRAR
Internal | 0
Internal % | 0%
Full % | 100%
External | NO BORRAR
External | 2
External % | 100%
Full % | 100%
Total
2